UNIVERSAL LEVEL ACTIVITIES:

SEPTEMBER-OCTOBER

VTPBiS AWARENESS:

1. Visit: www.pbisvermont.org	2.  Attend Leadership Forum Or view “Getting to Readiness” Webinar

VTPBiS ACTIVITIES FLOWCHART: 2015-2016

OCTOBER-JANUARY

UNIVERSAL READINESS ACTIVITIES:

- Establish Commitment

- Confirm both Administrator & SU Level Support & active involvement

- Include in top 3 school-wide goals

- Establish 80% commitment of staff

- Establish Leadership Team

- Identify a representative leadership team, including administration, and determine one member to serve as school-based coordinator

- Set effective team operating procedures, including regular meeting time

- Complete Readiness Checklist to 100% and complete Intent to Implement form

- Submit Intent to Implement by January 1 if planning to attend 2-Day Universal Training in March

or by April 1 if planning to attend 4-Day Universal Training in June

MARCH or JUNE

UNIVERSAL LEVEL TRAINING:

- Attending Universal Level Training:

  - Draft PBIS Implementation Plan to include:

    - Statement of Purpose

    - 3 to 5 school-wide behavioral expectations

    - Curriculum, lesson plans and schedule for teaching lessons

    - Teach the expectations

    - Process for discouraging problem behavior

    - Select a system for collecting and using data in decision-making

SEPTEMBER

ROLL-OUT ACTIVITIES:

- Conduct roll-outs for staff and school community

- Conduct roll-out for students and families

- Implement all parts of Implementation Plan

- Conduct leadership team meetings and report progress to staff/school community monthly

- PBIS School-based Coordinator attends regional meetings bi-monthly

OCTOBER or NOVEMBER

POST-IMPLEMENTATION:

- Conduct School-wide Evaluation (SET) six to eight weeks after roll-out

- If SET score of 80/80 is achieved, plan for targeted training.  If not, continue implementation plan.

TARGETED LEVEL ACTIVITIES: More Info: http://www.pbisvermont.org/events/targeted-training

JANUARY-MARCH OR APRIL-JUNE

FIRST STEPS MODULE SERIES:

- Complete the VTPBiS First Steps to Implementation online module series.

- Register and pay for your team to attend one of the trainings if you haven’t already done so;

- Complete your School-wide Evaluation Tool (SET) prior to attendance at the training;

- Prepare your school staff to complete the online Self-Assessment Survey (SAS).

INTENSIVE LEVEL ACTIVITIES: More Info: http://www.pbisvermont.org/events/intensive-training