## Sheet1
2016 | FEBRUARY (Catalog) | MARCH | APRIL | MAY | JUNE (Scribing) | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | 2017 | JANUARY | FEBRUARY (Catalog) | MARCH | APRIL | MAY | JUNE | JULY (GO LIVE) | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | 2018 | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
SCRIBE | - Do analysis of what needs to be written in grand spreadsheet - Pull # of catalog years represented by student body - Decide on catalog years that need to be coded |  | - Examples get handed to Ellucian | - Ellucian codes examples - Create plan/timeline for coding major/minor/conc./prog - SCRIBE mjrs/minors/concs/degree programs |  |  |  | - Process prior exception/substitutions for older cat. years | - Train units to process exceptions/substitutions | [8 empty] | - Maintenance after go-live update coding for future catalogs | - Scribe complete
PROJECT MANAGEMENT | - Publish project charter - Categorize stakeholders for communication plan organization - Create project timeline - Create meetings schedule - Schedule Ellucian training sessions - Send task list reminders | - Build communication plan / Publish project plan timeline - Publish project charter | - Hire full-time coder |  |  | - Roll out plans for rest of colleges |  | - CEMS sign off (AD/Dean) - Discuss designing measures to capture usage | - CEMS Go Live
DESIGN |  |  | - Articulate/communicate choices for audit design - Include students in audit design - Include faculty in audit design - Include SS staff in audit design | - Reach agreement on unified format |  |  |  | - Identify/decide on format for Sep |  |  |  |  | - Identify/decide on formats for TE
COMMUNICATION | - Communicate project objectives, scope, and timeline to UVM constituents - Hold project launch meeting | - Build website for project | - SGA promoting benefits to students - Send project updates to key stakeholders - Schedule specialized info/PR with key stakeholders - Offer info sessions |  |  |  | - Update comm plan - Build SEP comm plan |  | - Build TE comm plan |  |  |  |  | - Update comm plan
IT/INSTALL | - Schedule product installs | - CS Server Creation - Prep IT Staff (training) - Install Degree Works - Test DW install for functionality | - Decide on frequency of DW feed |  |  |  | - Install student educational planner | - Test student ed planner for functionality |  | - Install transfer equivalency module | - Test transfer module for functionality
ASSESSMENT |  |  |  |  | - Verify quality of scribing |  |  | - Test product before go-live |  | - Capture usage data | [8 empty] | - Assessment of successes | - examine DW output file research opportunities with OIR | [5 empty] | JULY: - Assessment complete